## WBS with Gantt Chart
PROJECT TITLE | API & 웹 크롤링 활용 공공기관 대출상품 추천 및 적격 여부 판단
PROJECT MANAGER
COMPANY NAME
DATE | 2023-10-18 ~ 2023-11-01 | [5 empty] | PHASE ONE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Leon W | 2022-03-12 | 2022-03-15 | 3 | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2022-03-15 | 2022-03-16 | 1 | 100%
1.2 | Research | Pete S | 2022-03-15 | 2022-03-21 | 6 | 90%
1.3 | Projections | Steve L | 2022-03-16 | 2022-03-22 | 6 | 40%
1.4 | Stakeholders | Allen W | 2022-03-17 | 2022-03-22 | 5 | 70%
1.5 | Guidelines | Malik M | 2022-03-18 | 2022-03-22 | 4 | 60%
1.6 | Project Initiation | Malik M | 2022-03-23 | 2022-03-23 | 0 | 50%
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Steve L | 2022-03-24 | 2022-03-28 | 4 | 5%
2.2 | Budget | Allen W | 2022-03-29 | 2022-04-02 | 4 | 30%
2.3 | Communication Plan | Malik M |  |  | 0 | 0%
2.4 | Risk Management | Malik M |  |  | 0 | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking | Pete S |  |  | 0 | 0%
3.2 | KPIs | Leon W |  |  | 0 | 0%
3.2.1 | Monitoring | Kylie R |  |  | 0 | 0%
3.2.2 | Forecasts | Kylie R |  |  | 0 | 0%
3.3 | Project Updates | Pete S |  |  | 0 | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  | 0 | 0%
4.2 | Quality Deliverables | Allen W |  |  | 0 | 0%
4.3 | Effort & Cost Tracking | Malik M |  |  | 0 | 0%
4.4 | Project Performance | Malik M |  |  | 0 | 0%
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])

## WBS with Gantt Chart - 전세
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | API & 웹 크롤링 활용 공공기관 대출상품 추천 및 적격 여부 판단
TEAM LEADER | 오경환
TEAM NAME | Hip Data
DATE | 2023-10-18 ~ 2023-11-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | MEMO | % of TASK | WEEK 1 |  |  | WEEK 2 |  |  |  |  | WEEK 3
[6 empty] | COMPLETE | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1
착수
1 | 요구사항 분석 | - | 2023-10-18 | 좌동 |  | 0%
2 | 수행범위 정의 | - | 2023-10-18 | - |  | 0%
3 | 프로젝트 일정계획 수립 | - | 2023-10-18 | - |  | 0%
4 | 수행계획서 작성 | 박하민 | 2023-10-18 | - |  | 0%
5 |  |  | 2023-10-18 |  |  | 0%
6 |  |  | 2023-10-18 |  |  | 0%
7 |  |  | 2023-10-18 |  |  | 0%
분석
5 | 개발환경 작성 | - | 2023-10-18 | - |  | 0%
6 | 프로젝트 범위 확인 | - | 2023-10-18 | - |  | 0%
10 | [5 empty] | 0%
11 | [5 empty] | 0%
설계
7 | 정보구조 설계 | - | 2023-10-19 | 2023-10-20 |  | 0%
8 | 화면구조 설계 | - | 2023-10-19 | 2023-10-20 |  | 0%
9 | 데이터 수급 | 남지영, 신영화 | 2023-10-23 | 2023-10-24 | 질문/답변 자연어 데이터 | 0%
10 | 기능버튼 설계 | 박하민, 정종문 | 2023-10-25 | 2023-10-26 |  | 0%
11 | 사용자 화면 설계 | 오경환 | 2023-10-25 | 2023-10-26 |  | 0%
17 | [5 empty] | 0%
18 | [5 empty] | 0%
12 | 테스트 | - | 2023-10-27 | 2023-10-31 | 디버깅 | 0%
13 | 최종 보고서 작성 | 남지영, 신영화 | 2023-10-31 | 좌동 |  | 0%
14 | 발표 | 정종문 | 2023-11-01 | - |  | 0%
※ 개발노트 : 목적, 알고리즘, 보완사항(lesson learned)
※ - : 모든 팀원 함께 작업

## WBS with Gantt Chart - 녹색금융
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | 소비 패턴에 따른 녹색금융 추천 서비스
TEAM NAME | Hip Data
MEMBERS | 오경환(Leader), 남지영, 박하민, 신영화, 정종문
DATE | 2023-10-18 ~ 2023-11-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | MEMO | % of TASK | WEEK 1 |  |  | WEEK 2 |  |  |  |  | WEEK 3
[6 empty] | COMPLETE | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1
착수
1 | 요구사항 분석 | - | 2023-10-18 | 좌동 |  | 0%
2 | 수행범위 정의 | - | 2023-10-18 | - |  | 0%
3 | 프로젝트 일정계획 수립 | - | 2023-10-18 | - |  | 0%
4 | 수행계획서 작성 | 박하민 | 2023-10-18 | - |  | 0%
5 |  |  | 2023-10-18 |  |  | 0%
6 |  |  | 2023-10-18 |  |  | 0%
7 |  |  | 2023-10-18 |  |  | 0%
분석
5 | 개발환경 작성 | - | 2023-10-18 | - |  | 0%
6 | 프로젝트 범위 확인 | - | 2023-10-18 | - |  | 0%
10 | [5 empty] | 0%
11 | [5 empty] | 0%
설계
7 | 정보구조 설계 | - | 2023-10-19 | 2023-10-20 |  | 0%
8 | 화면구조 설계 | - | 2023-10-19 | 2023-10-20 |  | 0%
9 | 데이터 수급 | 남지영, 신영화 | 2023-10-23 | 2023-10-24 | 질문/답변 자연어 데이터 | 0%
10 | 기능버튼 설계 | 박하민, 정종문 | 2023-10-25 | 2023-10-26 |  | 0%
11 | 사용자 화면 설계 | 오경환 | 2023-10-25 | 2023-10-26 |  | 0%
17 | [5 empty] | 0%
18 | [5 empty] | 0%
12 | 테스트 | - | 2023-10-27 | 2023-10-31 | 디버깅 | 0%
13 | 최종 보고서 작성 | 남지영, 신영화 | 2023-10-31 | 좌동 |  | 0%
14 | 발표 | 정종문 | 2023-11-01 | - |  | 0%
※ 개발노트 : 목적, 알고리즘, 보완사항(lesson learned)
※ ( - ) : 모든 팀원 함께 작업

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.